## Warialda Memorial Pool
Item | Supplier | Unit | Unit Value exc | On cost | Total including | Qty | Total | Comments
Demolition | AC & HJ Rose | As per quotation | 7272.73 | 654.5457 | 7927.2757 | 1 | 7927.2757
Site establishment and security | Gwydir Shire Council | Estimate | 1500 | 0 | 1500 | 1 | 1500
Earthworks and site preparation | AC & HJ Rose | Estimate | 5000 | 450 | 5450 | 1 | 5450
Concrete | Inverell Aggregate | m3 | 238 | 21.42 | 259.42 | 40 | 10376.8
Mesh | McGregor Gourlay | sheet | 74 | 6.66 | 80.66 | 20 | 1613.2
Windows | Sapphire City Glass | As per quotation | 5383.64 | 484.5276 | 5868.1676 | 1 | 5868.1676
Concrete Blocks | Inverell Building Supplies | Estimate | 53120.45 | 4780.8405 | 57901.2905 | 1 | 57901.2905
Plumbing Materials | Reece | As per quotation | 9356.87 | 842.1183 | 10198.9883 | 1 | 10198.9883
Vinyl | Carpet Court | As per quotation | 18145.45 | 1633.0905 | 19778.5405 | 1 | 19778.5405
Roofing and walls Panel | Inverell Building Baagain Centre | As per quotation | 49927.05 | 4493.4345 | 54420.4845 | 1 | 54420.4845
Electrical installation | Warialda Electrical | As per quotation | 9577.27 | 861.9543 | 10439.2243 | 1 | 10439.2243
Structural steel & reinforcement | McGegor Gourley | Estimate | 6500 | 585 | 7085 | 1 | 7085
Laying of blocks | Doug Higgins Bricklaying | Block | 3 | 0.27 | 3.27 | 3562 | 11647.74
Plumbing installation | S&M Egan | As per quotation | 15000 | 1350 | 16350 | 1 | 16350
Signage | Visualise | Estimate | 1000 | 90 | 1090 | 1 | 1090
Signage | Al's signs & lines | Estimate | 750 | 67.5 | 817.5 | 1 | 817.5
Labour | Gwydir Shire Council | Week | 3577.7 | 1717.296 | 5294.996 | 10 | 52949.96 | 10 Weeks for 3 Men
Toilet & shower partitions | High Style Furniture & Kitchens | As per quotation | 51476.36 | 4632.8724 | 56109.2324 | 1 | 56109.2324
Kitchen equipment & exhaust canopy | Faircloth & Reynolds | As per quotation | 14910 | 1341.9 | 16251.9 | 1 | 16251.9
Internal plant | Gwydir Shire Council | week | 325 | 0 | 325 | 10 | 3250
Change room bench seating | Landmark Furphy | Estimate | 860 | 77.4 | 937.4 | 4 | 3749.6
Core filling of concrete blocks | Gwydir Shire Council | Estimate | 2500 | 0 | 2500 | 1 | 2500
Tiles & Accessories | Inverell Ceramics | Estimate | 4500 | 405 | 4905 | 1 | 4905
[7 empty] | 354252.6281 | TOTAL
Note: Estimate is exclusive of GST but is inclusive of Council oncosts | [6 empty] | 70850.5256 | 20% Contingency
[7 empty] | 425103.1537 | Grand Total

## Warialda Rec Ground Function Ce
Item | Supplier | Unit | Unit Value exc | On cost | Total including | Qty | Total | Comments
Demolition & preparation of building pad | AC & HJ Rose | Estimate | 10000 | 900 | 10900 | 1 | 10900
Site establishment and security | Gwydir Shire Council | Estimate | 1000 |  | 1000 | 1 | 1000
Concrete | Inverell Aggregate | m3 | 238 | 21.42 | 259.42 | 35 | 9079.7 | Travel Inc
Mesh | McGregor Gourlay | sheet | 74 | 6.66 | 80.66 | 20 | 1613.2
Windows & Bi -Fold Door | Sapphire City Glass | As per quotation | 6347.64 | 571.2876 | 6918.9276 | 1 | 6982.4 | 4 windows 1 Door
Shed | Armidale Titan Shed | kit | 16182 | 1456.38 | 17638.38 | 1 | 17638.38
Plumbing Materials | Reece Plumbing | As per quotation | 17464.34 | 1571.7906 | 19036.1306 | 1 | 19210.78
Vinyl | Carpet Court | As per quotation | 10088 | 907.92 | 10995.92 | 1 | 10995.92
Cool Room | Ben Green | As per quotation | 13300 | 1197 | 14630 | 1 | 14630 | Supply and Install
Labour | Gwydir Shire Council | Week | 3577.7 | 1717.296 | 5294.996 | 10 | 52949.96 | 10 Weeks for 3 Men
Trench Mesh | McGregor Gourlay | 120m | 22 | 1.98 | 23.98 | 20 | 479.6
Bar Chairs | McGregor Gourlay | Bag | 20 | 1.8 | 21.8 | 4 | 87.2
Shed Lining & Awning | Inverell Building Baaagain Centre | As per quotation | 30000.35 | 6416.03 | 36416.38 | 1 | 36416.38
Electrical | WE Warialda Electrical | As per quotation | 8015 | 801.5 | 8816.5 | 1 | 8816.5
Black Plastic | McGregor Gourlay | Roll | 100 | 10 | 110 | 3 | 330
Aluminium Seats | Landmark Furphy | As per quotation | 950 | 95 | 1045 | 10 | 10450
Plumbing installation | S&M Egan | As per quotation | 5000 | 95 | 5095 | 1 | 5095
Internal plant | Gwydir Shire Council | week | 325 | 0 | 325 | 10 | 3250
Servery benches | High Style Furniture & Kitchens | As per quotation | 5695.45 | 512.5905 | 6208.0405 | 1 | 6208.0405
Signage | Al's signs & lines | Estimate | 500 | 45 | 545 | 1 | 545
Steel for awning | McGregor Gourlay | Estimate | 1650 | 148.5 | 1798.5 | 1 | 1798.5
[7 empty] | 218476.5605 | TOTAL
Note: Estimate is exclusive of GST but is inclusive of Council oncosts | [6 empty] | 43695.3121 | 20% Contingency
[7 empty] | 262171.8726 | Grand Total

## Bingara Sporting Club Change Ro
Item | Details
Demolition & prep | All demolition, isolation of site, signage and barracading
Plumbing fixtures | Showers x 1, Single wall vanity and tapware in womens W.C., toilets x 1
Tiles | Large format tiles, floor to ceiling in Shower. Large format floor tiles in womens W.C., shower room and hallway.
Partitions | Laminate shower partition including an alcove with a bench requires in the shower cubicles.
Plumbing installation (Labour) | Any cutting of existing subfllor drainage or plumbing. Installation of All new drainage and PC items
Plumbing materials | Pipes, drainage. Water proofing etc
Plumbing internal plant | Any necxessary machinery hire
Internal fixtures and fittings | Mirrors, towel racks for showers, toilet roll holder, soap dish in showers, soap dispenser, paper towel dispenser.
Building Labour | All labour for demolition and construction
Building materials | All building material including any timber for walls, sheeting.
Signage | For front door (Change rooms) and male and female for each entry.
Building internal plant | Any necessary hire of equipment for deomiltion and or constrcution
Lighting & electrical installation | Lighting for all areas inclusing down lighting over vanities, exhaust fans, electric hand dryers and power points accessible for use near Vanitie
Other notes | Any interruption to power supply or other services, access and or the ability trade must be communicated with the project Manager, the Sporting Club Manager and the Lessee of the Chinese restaurant.
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  |  | 0 | TOTAL
Note: Estimate is exclusive of GST but is inclusive of Council oncosts |  |  | 0
|  |  | 0 | Grand Total